## Gantt Chart
MATE ROV Gantt Chart
PROJECT TITLE |  | Oceanus |  |  |  |  | COMPANY NAME | [9 empty] | ThinkTank
PROJECT MANAGER |  | Emily Bass Werner & Zack Hobbs |  |  |  |  | DATE | [9 empty] | 2025-06-06
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [9 empty] | PHASE TWO | [7 empty] | PHASE THREE
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10
[7 empty] | S | M | T | W | R | F | St | S | M | T | W | R | F | St | S | M | T | W | R | F | St | S | M | T | W | R | F | St | S | M | T | W | R | F | St | S | M | T | W | R | F | St | S | M | T | W | R | F | St | S | M | T | W | R | F | St | S | M | T | W | R | F | St | S | M | T | W | R | F | St
F2025 | Phase B: Preliminary Design & Technology Completion
1.1 | Trade Studies | Everyone | 2025-09-28 | 2025-10-11 | 13 | 100% | bar: WEEK 1 S to WEEK 2 St
1.2.1 | TMS Prototype #3 | TMS | 2025-09-28 | 2025-10-11 | 13 | 100% | bar: WEEK 1 S to WEEK 2 St
1.2.2 | F&P Prototype #3 | F&P | 2025-09-28 | 2025-10-11 | 13 | 100% | bar: WEEK 1 S to WEEK 2 St
1.2.3 | C&C Prototype #3 | C&C | 2025-09-28 | 2025-10-08 | 10 | 100% | bar: WEEK 1 S to WEEK 2 St
1.2.4 | GNC Prototype #3 | GNC | 2025-09-28 | 2025-10-04 | 6 | 100% | bar: WEEK 1 S to WEEK 2 St
1.2.5 | EPS Prototype #3 | EPS | 2025-10-03 | 2025-10-11 | 8 | 100% | bar: WEEK 1 S to WEEK 2 St
1.1.1 | Preliminary Design Review | Everyone | 2025-10-12 | 2025-10-25 | 13 | 100%
1.2 | Prototype #1 Presentation | Everyone | 2025-10-26 | 2025-10-26 | 0 | 100% | bar: WEEK 2 S to WEEK 5 St
1.2.1 | TMS Prototype #1 | TMS | 2025-10-27 | 2025-10-27 | 0 | 100% | bar: WEEK 2 S to WEEK 5 St
1.2.2 | F&P Prototype #1 | F&P | 2025-10-28 | 2025-10-28 | 0 | 100% | bar: WEEK 2 S to WEEK 5 St
1.2.3 | C&C Prototype #1 | C&C | 2025-10-29 | 2025-10-29 | 0 | 100% | bar: WEEK 2 S to WEEK 5 St
1.2.4 | GNC Prototype #1 | GNC | 2025-10-30 | 2025-10-30 | 0 | 100% | bar: WEEK 2 S to WEEK 5 St
1.2.5 | EPS Prototype #1 | EPS | 2025-10-31 | 2025-10-31 | 0 | 100% | bar: WEEK 2 S to WEEK 5 St
1.3 | Detailed Design Review | Everyone | 2025-10-27 | 2025-11-15 | 18 | 100% | bar: WEEK 6 S to WEEK 8 St
1.3.1 | TMS Prototype #2 | TMS | 2025-10-27 | 2025-10-27 | 0 | 100% | bar: WEEK 6 S to WEEK 8 St
1.3.2 | F&P Prototype #2 | F&P | 2025-10-28 | 2025-10-28 | 0 | 100% | bar: WEEK 6 S to WEEK 8 St
1.3.3 | C&C Prototype #2 | C&C | 2025-10-29 | 2025-10-29 | 0 | 100% | bar: WEEK 6 S to WEEK 8 St; WEEK 10 F to WEEK 10 St
1.3.4 | GNC Prototype #2 | GNC | 2025-10-30 | 2025-10-30 | 0 | 100% | bar: WEEK 6 S to WEEK 8 St; WEEK 10 F to WEEK 10 St
1.3.5 | EPS Prototype #2 | EPS | 2025-10-31 | 2025-10-31 | 0 | 100% | bar: WEEK 6 S to WEEK 8 St; WEEK 10 F to WEEK 10 St
1.4 | Prototype #2 Presentation | Everyone | 2025-11-16 | 2025-11-16 | 0 | 100% | bar: WEEK 10 F to WEEK 10 St
1.6 | EoS | Everyone | 2025-11-30 | 2025-11-30 | 0 | 0% | bar: WEEK 9 S to WEEK 9 St; WEEK 10 F to WEEK 10 St
1.7 | Envision Outreach Event | Everyone | 2025-06-17 | 2025-06-17 | 0 | 0%
S2026 | Phase C: Final Design
2.1 | BoM & ConOps | Managers | 2025-12-13 | 2026-01-12 | 29 | 0% | bar: WEEK 1 S to WEEK 4 St
2.2 | CDR | Everyone | 2025-06-18 | 2025-06-25 | 7 | 0% | bar: WEEK 1 S to WEEK 4 St
1.2.1 | TMS Prototype #3 | TMS | 2025-10-27 | 2025-10-27 | 0 | 0% | bar: WEEK 1 S to WEEK 4 St
1.2.2 | F&P Prototype #3 | F&P | 2025-10-28 | 2025-10-28 | 0 | 0% | bar: WEEK 1 S to WEEK 4 St
1.2.3 | C&C Prototype #3 | C&C | 2025-10-29 | 2025-10-29 | 0 | 0% | bar: WEEK 1 S to WEEK 4 St
1.2.4 | GNC Prototype #3 | GNC | 2025-10-30 | 2025-10-30 | 0 | 0% | bar: WEEK 1 S to WEEK 4 St
1.2.5 | EPS Prototype #3 | EPS | 2025-10-31 | 2025-10-31 | 0 | 0% | bar: WEEK 1 S to WEEK 4 St
2.3 | Writing Fabrication Procedure | Everyone | 2025-06-18 | 2025-06-25 | 7 | 0% | bar: WEEK 4 S to WEEK 5 St
2.4 | Fluids Quiz | Everyone | 2025-06-18 | 2025-06-25 | 7 | 0% | bar: WEEK 6 S
2.5 | Fabrication & Testing | Managers | 2025-06-22 | 2025-06-22 | 0 | 0% | bar: WEEK 6 S to WEEK 10 St
2.6 |  | Everyone | 2025-06-18 | 2025-06-25 | 7 | 0%
2.7 |  |  | 2025-06-18 | 2025-06-25 | 7 | 0%
2.8 |  |  | 2025-06-18 | 2025-06-25 | 7 | 0%
2.9 |  |  | 2025-06-18 | 2025-06-25 | 7 | 0%
S2026 | Phase C: Final Design Fabrication
3.1 |  | Everyone | 2025-06-26 | 2025-07-02 | 6 | 0%
3.1.1 |  | Managers | 2025-06-29 | 2025-06-29 | 0 | 0%
3.2 |  | Managers | 2025-06-29 | 2025-06-29 | 0 | 0%
3.1.2 |  | Everyone | 2025-07-02 | 2025-07-03 | 1 | 0%
3.1.3 |  | Everyone | 2025-07-03 | 2025-07-03 | 0 | 0%
3.1.4 |  | Managers | 2025-07-04 | 2025-07-04 | 0 | 0%
3.2.1 |  | Managers | 2025-07-04 | 2025-07-04 | 0 | 0%
3.3 |  | Everyone | 2025-07-07 | 2025-07-11 | 4 | 0%
3.3.1 |  | Everyone | 2025-07-09 | 2025-07-09 | 0 | 0%
3.3.2 |  | Everyone | 2025-07-11 | 2025-07-12 | 1 | 0%
3.3.3 |  | Everyone | 2025-07-12 | 2025-07-13 | 1 | 0%
3.2.3 |  | Managers | 2025-07-14 | 2025-07-14 | 0 | 0%
3.3.4 |  | Managers | 2025-07-14 | 2025-07-14 | 0 | 0%
4
4.1 |  |  |  |  | 0 | 0%
4.2 |  |  |  |  | 0 | 0%
4.3 |  |  |  |  | 0 | 0%
4.4 |  |  |  |  | 0 | 0%